## Sheet1
Day | Time | Location | What we did | What will be done next time | Did we accomplish what we were supposed to?
2018-03-14 | 9-10 am | LEEP2 | Set-up repository, created gant chart | Party during spring break | N/A
|  |  | Initial Planning | Do basic unity tutorials
2018-03-26 | 3-4:30 pm | LEEP2 | Planned rest of project | Choose sprite sheet we would like | Yes
and start working on map generation
2018-03-27 | 5:00-7:30 pm | LEEP2 | Chose sprites we wanted to use for the map | Finish map gerneration and start working on characters and | Yes
|  |  | Started working on Proedural generation | game logic.
2018-04-01 | 9:00 - 11:00 pm | LEEP2 | Made progress on map generation | Meet after class and polish off map generation | No
Found bugs causing the map to not generate correctly
2018-04-02 | 9:00 - 10:00 am | LEEP2 | Worked on fixing generation when stuck | Continue with fixing it getting stuck | No
2018-04-02 | 8:00 - 10:00 pm | LEEP2 | Finished map generation | Level iteration screen | Yes
2018-04-03 | 5:30 - 7:00 pm | LEEP2 | Level Iteration logic | Home screen and player UI | Yes
2018-04-04 | 9:00 - 10:00 am | LEEP2 | Start merging map anc characters | continue merging map and character
2018-04-06 | 7:00 - 10:00 pm | LEEP2 | Merge map and characters | continue merging map and character | Yes
2018-04-07 | 4:00 - 10:00 pm | LEEP2 | Merge map and characters | Continue with merging | No
2018-04-08 | 2:00 - pm | LEEP2 | Finalize merging and finish attack | Stage 1 | Yes
2018-04-11 | 9:00 - 10:00 am | LEEP2 | Talked about new features | Start working on new features/add animations | N/A
2018-04-11 | 3:00-4:30 pm | LEEP2 | Talked about new features | Start working on new features/add animations | Yes
2018-04-16 | 9:00 - 10:00 am | LEEP2 | Added animations and started on level progression | Finish Level Generation | Yes
2018-04-18 | 9:00 - 10:00 am | LEEP2 | Finished Level Progression | Add Item Interaction | Yes
2018-04-23 | 9:00 - 10:00 am | LEEP2 | Finished item interaction and started pause menu | Pause Menu finished, add music | Yes
| 9:00 - 10:00 am | LEEP2 | Finished pause menu and made progress on music | Finish with music and implement new players | Yes