## real Gantt Chart
Task | Start Date | End Date | Duration
Gather requirements | 2018-03-14 | 2018-03-19 | 2
Learn Unity/C#/Sprites | 2018-03-16 | 2018-03-27 | 10
Code Map | 2018-03-26 | 2018-04-17 | 7
Code Players/Enemies | 2018-03-28 | 2018-04-03 | 7
Home, Character, Level UI | 2018-04-02 |  | 2
Merge Characters and map | 2018-04-04 | 2018-04-15 | 4
Game Balancing |  | 1900-01-10
Debug/Test |  | 1900-01-01
Publish Project |  | 1900-01-13
Initial source: https://www.ablebits.com/office-addins-blog/2014/05/23/make-gantt-chart-excel/
Formulas:
End Date = [Start Date]+5

## projected Gantt Chart
Task | Start Date | End Date | Duration
Gather requirements | 2018-03-14 | 2018-03-19 | 2
Learn Unity/C#/Sprites | 2018-03-16 | 2018-03-27 | 10
Code Map | 2018-03-26 | 2018-04-17 | 3
Code Players/Enemies | 2018-03-28 | 2018-04-03 | 5
Game Balancing | 2018-04-01 | 2018-04-12 | 4
Debug/Test | 2018-04-04 | 2018-04-15 | 3
Publish Project | 2018-04-07 | 2018-04-09 | 1
1900-01-13
1900-01-05
Initial source: https://www.ablebits.com/office-addins-blog/2014/05/23/make-gantt-chart-excel/
Formulas:
End Date = [Start Date]+5